## Sheet1
Timeline
Dates |  | Task
October 28th 2019 |  | Finish the Project Proposal
November 4th 2019 |  | Finish the basic outline and the layout of our app as well as basic ux and ui tools. As well should have the basic tasks like setting up the github project and someone to host the program.
November 8th 2019 |  | We should be able to get all of the forecast and weather alert data that is needed for the application and for it to be able to display in the ui
November 15th 2019 |  | We should be able to display all of the data that is being used by the page and we should be able to display a basic radar map. We should also be able to send push notifications.
November 18th 2019 |  | Be able to run the program without worring about errors and crashing. Begin to work on the customization features like automatic location and custom locations
November 25th 2019 |  | Continue working on fixing any issues and working on adding the small features that are considered secondary to the primary features.
November 26th 2019 |  | Finish the features need and finalize the UI and UX. Continue to polish bugs and other features.
December 13th 2019 |  | Submit the final project (this includes the team folder for the presentation, the final report and the powerpoint.